## Cover
Rivanta General Insurance
Group Technology — FY2026 Budget vs Actuals
Prepared for: Board Technology & Risk Committee (BTRC)
Owner: Office of the Group CTO
Reporting period: Q1 FY2026 (1 Jan – 31 Mar 2026). FY2026 full-year budget shown for context.
Sheets in this workbook
1. Monthly_PnL — 12-month tech budget vs actual by cost centre
2. CostCentres — reference list of IT cost centres and owners
3. ProjectStatus — strategic project portfolio status
Notes
• All figures in RM '000 unless stated otherwise.
• Variance is calculated as Actual minus Budget. Positive = over budget (adverse).
• 10% adverse variance triggers a mandatory Tech Steering corrective action plan.

## CostCentres
Cost Centre Code | Cost Centre | Pillar | Owner / Head
CC-101 | Core Insurance Platform | Applications | Head of Core Systems
CC-102 | Claims & Underwriting Tech | Applications | Head of Claims Tech
CC-103 | Digital Distribution & Portals | Applications | Head of Digital
CC-104 | Data & Analytics Platform | Data & AI | Head of Data
CC-105 | Cybersecurity Operations | Cyber & Resilience | Group CISO
CC-106 | Cloud & Infrastructure | Infrastructure | Head of Infrastructure
CC-107 | End User Computing & Service Desk | Workplace IT | Head of Workplace IT
CC-108 | Network & Telephony | Infrastructure | Network Manager
CC-109 | IT Vendor & Contract Management | Tech Governance | Head of Vendor Mgmt
CC-110 | Tech Risk & RMiT Compliance | Tech Governance | Head of Tech Risk
CC-111 | Innovation & AI Lab | Data & AI | Head of Innovation
CC-112 | PMO & Project Delivery | Tech Governance | Head of PMO

## Monthly_PnL
Cost Centre Code | Cost Centre | Pillar | Owner | Annual Budget (RM '000) | Budget Jan | Actual Jan | Budget Feb | Actual Feb | Budget Mar | Actual Mar | Budget Apr | Actual Apr | Budget May | Actual May | Budget Jun | Actual Jun | Budget Jul | Actual Jul | Budget Aug | Actual Aug | Budget Sep | Actual Sep | Budget Oct | Actual Oct | Budget Nov | Actual Nov | Budget Dec | Actual Dec | YTD Budget | YTD Actual | YTD Variance | Variance % | RAG
CC-101 | Core Insurance Platform | Applications | Head of Core Systems | 28800 | 2370.4 | 2417.8 | 2251.9 | 2364.5 | 2488.9 | 2688 | 2370.4 |  | 2370.4 |  | 2488.9 |  | 2370.4 |  | 2370.4 |  | 2488.9 |  | 2370.4 |  | 2370.4 |  | 2488.9 |  | 7111.2 | 7470.3 | 359.1 | 5.05% | Amber
CC-102 | Claims & Underwriting Tech | Applications | Head of Claims Tech | 8400 | 691.4 | 677.6 | 656.8 | 656.8 | 725.9 | 740.4 | 691.4 |  | 691.4 |  | 725.9 |  | 691.4 |  | 691.4 |  | 725.9 |  | 691.4 |  | 691.4 |  | 725.9 |  | 2074.1 | 2074.8 | 0.7 | 0.03375% | Green
CC-103 | Digital Distribution & Portals | Applications | Head of Digital | 6600 | 543.2 | 521.5 | 516 | 505.7 | 570.4 | 570.4 | 543.2 |  | 543.2 |  | 570.4 |  | 543.2 |  | 543.2 |  | 570.4 |  | 543.2 |  | 543.2 |  | 570.4 |  | 1629.6 | 1597.6 | -32 | -1.964% | Green
CC-104 | Data & Analytics Platform | Data & AI | Head of Data | 7200 | 592.6 | 622.2 | 563 | 619.3 | 622.2 | 696.9 | 592.6 |  | 592.6 |  | 622.2 |  | 592.6 |  | 592.6 |  | 622.2 |  | 592.6 |  | 592.6 |  | 622.2 |  | 1777.8 | 1938.4 | 160.6 | 9.034% | Amber
CC-105 | Cybersecurity Operations | Cyber & Resilience | Group CISO | 9600 | 790.1 | 790.1 | 750.6 | 765.6 | 829.6 | 871.1 | 790.1 |  | 790.1 |  | 829.6 |  | 790.1 |  | 790.1 |  | 829.6 |  | 790.1 |  | 790.1 |  | 829.6 |  | 2370.3 | 2426.8 | 56.5 | 2.384% | Green
CC-106 | Cloud & Infrastructure | Infrastructure | Head of Infrastructure | 12000 | 987.7 | 1027.2 | 938.3 | 985.2 | 1037 | 1099.2 | 987.7 |  | 987.7 |  | 1037 |  | 987.7 |  | 987.7 |  | 1037 |  | 987.7 |  | 987.7 |  | 1037 |  | 2963 | 3111.6 | 148.6 | 5.015% | Amber
CC-107 | End User Computing & Service Desk | Workplace IT | Head of Workplace IT | 4800 | 395.1 | 375.3 | 375.3 | 360.3 | 414.8 | 402.4 | 395.1 |  | 395.1 |  | 414.8 |  | 395.1 |  | 395.1 |  | 414.8 |  | 395.1 |  | 395.1 |  | 414.8 |  | 1185.2 | 1138 | -47.2 | -3.982% | Green
CC-108 | Network & Telephony | Infrastructure | Network Manager | 3600 | 296.3 | 290.4 | 281.5 | 278.7 | 311.1 | 311.1 | 296.3 |  | 296.3 |  | 311.1 |  | 296.3 |  | 296.3 |  | 311.1 |  | 296.3 |  | 296.3 |  | 311.1 |  | 888.9 | 880.2 | -8.7 | -0.9787% | Green
CC-109 | IT Vendor & Contract Management | Tech Governance | Head of Vendor Mgmt | 1800 | 148.1 | 142.2 | 140.7 | 133.7 | 155.6 | 150.9 | 148.1 |  | 148.1 |  | 155.6 |  | 148.1 |  | 148.1 |  | 155.6 |  | 148.1 |  | 148.1 |  | 155.6 |  | 444.4 | 426.8 | -17.6 | -3.96% | Green
CC-110 | Tech Risk & RMiT Compliance | Tech Governance | Head of Tech Risk | 2400 | 197.5 | 217.3 | 187.7 | 210.2 | 207.4 | 238.5 | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 592.6 | 666 | 73.4 | 12.39% | Red
CC-111 | Innovation & AI Lab | Data & AI | Head of Innovation | 3000 | 246.9 | 259.2 | 234.6 | 258.1 | 259.3 | 290.4 | 246.9 |  | 246.9 |  | 259.3 |  | 246.9 |  | 246.9 |  | 259.3 |  | 246.9 |  | 246.9 |  | 259.3 |  | 740.8 | 807.7 | 66.9 | 9.031% | Amber
CC-112 | PMO & Project Delivery | Tech Governance | Head of PMO | 2400 | 197.5 | 193.5 | 187.7 | 185.8 | 207.4 | 207.4 | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 197.5 |  | 197.5 |  | 207.4 |  | 592.6 | 586.7 | -5.9 | -0.9956% | Green
| GROUP TOTAL |  |  | 90600

## ProjectStatus
Project Code | Project Name | Sponsor | Pillar | Approved Budget (RM '000) | Spent to Date (RM '000) | Forecast at Completion (RM '000) | Schedule Status | Risk Rating | Comment
PRJ-001 | Core Insurance Platform Modernisation | Group CEO | Applications | 18000 | 14200 | 21800 | Behind | HIGH | Vendor scope creep and integration delays. Re-baselined twice. RM 3.8m forecast overrun.
PRJ-002 | Claims Straight-Through Processing | COO | Applications | 5200 | 3100 | 5400 | On Track | MEDIUM | Pilot in motor claims live; expand to property Q4.
PRJ-003 | Customer Portal & Mobile Refresh | Chief Distribution Officer | Applications | 3600 | 2200 | 3700 | On Track | LOW | Phase 1 launched. Phase 2 in UAT.
PRJ-004 | Enterprise Data Platform (Lakehouse) | Group CFO | Data & AI | 6800 | 4900 | 8100 | Behind | HIGH | Cloud egress costs exceeded estimate. Vendor engaged on cost optimisation.
PRJ-005 | Generative AI for Underwriting Triage | Group CUO | Data & AI | 1500 | 1100 | 1700 | On Track | MEDIUM | Live with two underwriting teams. ROI being measured.
PRJ-006 | Cyber Resilience Uplift (RMiT 2024) | Group CISO | Cyber & Resilience | 4400 | 3500 | 5100 | Behind | HIGH | Incident response retainer renewed at higher rate. Two new BNM controls added in scope.
PRJ-007 | Cloud Migration Wave 2 | Head of Infrastructure | Infrastructure | 7200 | 5400 | 7600 | On Track | MEDIUM | Wave 2 70% complete. FX impact on USD-denominated cloud spend.
PRJ-008 | Workplace M365 / Copilot Rollout | COO | Workplace IT | 2200 | 1300 | 2150 | On Track | LOW | E5 + Copilot licences provisioned to Phase 1 cohort of 350.
PRJ-009 | Vendor Risk Management Platform | Head of Vendor Mgmt | Tech Governance | 900 | 450 | 920 | On Track | LOW | Implementation on schedule. Go-live Q1 next year.
PRJ-010 | RMiT Reporting Automation | Head of Tech Risk | Tech Governance | 1100 | 650 | 1180 | On Track | MEDIUM | Automating BNM RMiT periodic submissions. Phase 1 live.